## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Android Application Manager: Hu Yuang | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.1: Discuss and analyze user's requirement | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.2: Implement a basic Graphics User Interface | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.3: Implement Chat Dialog | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.4: After connection work (task 5) is done, test the app' core functions. | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.5: Add some extra features if it is necessary | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.6: Apply some beautiful elements to improve UI | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
Task 1.7:Test android application thoroughly. | Hu Yuang, Yang Jiarui, Chen Donglin | [16 empty] | Null
WP 2: Server Manager: Chen Donglin | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
Task 2.1: The Flask server could response a fundamental web page | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
Task 2.2: The Flask server could connect the database | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
Task 2.3: The server could connect to the APP | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
Task 2.4: User could login and access its personal information | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
Task 2.5: The server could response every request within 10ms | Chen Donglin, Hu Yuang, Wang Xinzhu | [16 empty] | Null
WP 3: WebPage Manager: Wang Xinzhu | Wang Xinzhu, Li Ziqi, Hu Yuang | [16 empty] | Null
Task 3.1: Design and implement the user interface of the web application | Wang Xinzhu, Li Ziqi, Hu Yuang | [16 empty] | Null
Task 3.2: Connect the web pages to database | Wang Xinzhu, Li Ziqi, Hu Yuang | [16 empty] | Null
Task 3.3: Test the work package implementation | Wang Xinzhu, Li Ziqi, Hu Yuang | [16 empty] | Null
WP 4: Database Manager: Chen Donglin | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
Task 4.1:Design the database | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
Task 4.2:Draw the database diagram | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
Task 4.3:Optimize the database performance | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
Task 4.4:Connect the database to the flask server | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
Task 4.5:Store website information to the server | Chen Donglin, Wang Xinzhu, Yang Jiarui | [16 empty] | Null
WP 5: Connection Manager: Hu Yuang | Hu Yuang, Li Ziqi, Yang Jiarui | [16 empty] | Null
Task 5.1: Implement and test the connection on android | Hu Yuang, Li Ziqi, Yang Jiarui | [16 empty] | Null
Task 5.2: Implement and test the connection on web. | Hu Yuang, Li Ziqi, Yang Jiarui | [16 empty] | Null
Task 5.3: Develop cache on android to buffer data transferred from server. | Hu Yuang, Li Ziqi, Yang Jiarui | [16 empty] | Null
Task 5.4: Develop cache on web to buffer data transferred from server on android | Hu Yuang, Li Ziqi, Yang Jiarui | [16 empty] | Null
WP 6: Authorization Manager: Yang Jiarui | Yang Jiarui, Li Ziqi, Chen Donglin | [16 empty] | Null
Task 6.1: Implement login interface | Yang Jiarui, Li Ziqi, Chen Donglin | [16 empty] | Null
Task 6.2: Implement login information corresponding to the database | Yang Jiarui, Li Ziqi, Chen Donglin | [16 empty] | Null
Task 6.3: Test the work package implementation | Yang Jiarui, Li Ziqi, Chen Donglin | [16 empty] | Null
WP 7: Online Chatting Manager: Li Ziqi | Li Ziqi, Wang Xinzhu, Chen Donglin | [16 empty] | Null
Task 7.1: Design and discuss server builds | Li Ziqi, Wang Xinzhu, Chen Donglin | [16 empty] | Null
Task 7.2:Design a interface | Li Ziqi, Wang Xinzhu, Chen Donglin | [16 empty] | Null
Task 7.3:Build a platform | Li Ziqi, Wang Xinzhu, Chen Donglin | [16 empty] | Null
Task 7.4:Design a special communication channel | Li Ziqi, Wang Xinzhu, Chen Donglin | [16 empty] | Null
Milestrone
Deliverable